## Eugenio 1
| INDIVIDUAL PERFORMANCE COMMITMENT AND REVIEW (IPCR) MFO-BASED PERFORMANCE | [5 empty] | RATING PERIOD: JANUARY - JUNE 2024
To be signed BEFORE the rating period.
I, ARCANGEL M. EUGENIO,Division Manager A , of the Field Operations Management Department, commit to deliver and agree to be rated on the attainment of the following targets in accordance with the indicated measures for the period JANUARY TO JUNE 2024. ARCANGEL M. EUGENIO Division Manager A | I hereby certify that the commitments stated herein were discussed/agreed with the ratee. RYAN JAMES V. AYSON Manager, Field Operations Management Department
MFOs AND PERFORMANCE INDICATORS | SUCCESS INDICATOR FY 2024 TARGETS | ACTUAL ACCOMPLISHMENTS | RATING |  |  |  | REMARKS
|  |  | Quality Q1 | Efficiency E2 | Timeliness T3 | Ave
A. Major Final Outputs (MFOs)/ Operations
MFO1: Uninterrupted and Adequate Supply and Distribution of Potable Water for Domestic Use in its Service Area
Performance Indicator 3: Management of the operations of Bulacan Bulk Water Supply Project
3.1 Assistance to the CMU in the Monitoring of commercial operations of Stage 1 & 2 | 100% verified compliance with all operational requirements of the Concessionaire under the CA for Stage 1 & 2. | 100% compliance
3.2 Availability of supply (capacity) based on average Minimum Committed Volume (MCV) | Meet or exceed the this period's average approved MCV | 100% compliance |  |  |  |  | MCV from previous year (CY 2023) = 192.93 MLD Approved MCV for CY 2024 = 192.93 MLD Actual average volume supplied during this period = 230.62 MLD
3.3 Annual Bulk Water Charge (BWC) Adjustment due to the current year's July-posted Consumer Price Index | MWSS BOT approval within the 3rd Quarter of this period | to be accomplished in the 3rd Quarter of the year |  |  |  |  | To be completed on the 2nd half of this period
3.41.1 Monitoring and provision of technical, administrative, legal and other needed project support on all related activities of the Project involving among others Detailed Engineering Design, civil works construction, permitting works and clearances, right-of-way acquisition/possession, ECC compliance monitoring. The BBWSP Stage 3a is composed of 3 components; Stage 3a-1 is the construction of pipe conveyance extension for Hagonoy and Pandi alignment; Stage 3a-2 is for the construction of the Norzagaray Water System including 10 MLD Water Treatment Plant; and Stage 3a-3 is for Angat-Bustos Water Supply System. The Stage 3a Project will provide potable water supply for the municipalities of Angat, Bustos, Hagonoy, Norzagaray, Pandi, Pulilan, San Ildefonso, San Miguel, San Rafael, Doña Remedios Trinidad and the City of Baliwag. | Stage 3a-1: 100% Overall Physical Accomplishment Stage 3a-2: 100% Overall Physical Accomplishment Stage 3a-3: 100% Completion of DED | Stage 3a-1 = 0% Stage 3a-2 = 0% Stage 3a-3 = 0% |  |  |  |  | MWSS BOT approved the request for Time Extension was approved on 07 December 2022 thru the BOT Resolution No. 2022-162-CO. No Physical accomplishment for this period due to the following reasons: 1. Failed bidding process - no contractor accepted the proposal; 2. Increase in construction materials and labor cost; 3. In-depth recalibration of the contract price. Nonetheless, MWSS BBWSP Project Team continued to follow-up on the progress of the project throughout this period.
3.5 BBWSP Stage 3 overall construction supervision and monitoring
MFO2: Operations and Maintenance of Water Supply and Sewerage Systems in its Service Area
Performance Indicator 1: Support to the Concessionaires in the implementation of water supply projects
1.1 Monitoring of Concessionaires' water supply projects | Bi-Monthly Report Submitted | Submission of Monitoring Report within 10 days from the receipt of report from the concessionnaires | RJVA/East and West Divisions Assigned Personnel |  |  |  | - Reviewed the bi-monthly reports prior to submission to ADA
1.1.2 East Zone downstream projects (MWCI) | Construction Monitoring with Progress Report Submittlas | Submission of Monthly Monitoring Report within 10 days from the receipt of report from the concessionnaires |  |  |  |  | -Reviewed and assisted in the timely preparation and submission of the Monthly Monitoring Report within 10 days from receipt of the concessionnaires’ report. Consolidate submitted partial report from MWCI to send the ADA of ETOG.
1.1.3 Conduct regular on-site inspections to validate accomplishments of the ongoing projects of the concessionnaires | Accomplishment monitoring and verification on site | Submission of Quarterly Inspection Report |  |  |  |  | -Verified progress of ongoing concessionaire projects. -Conducted site inspections to verify actual project outputs against approved work plans and milestones. -Reviewed formal inspection reports for distribution to project piror to submission to DM.
1.2 Monitoring of concessionaires deepwell operations | Bi-Monthly Report Submitted | Submission of Monitoring Report within 10 days from the receipt of report from the concessionnaires |  |  |  |  | -Reviewed monitoring prior to submission of letter to NWRB
1.3 Address stakeholder concerns relative to the implementation and operation of water supply. | Endorsed complaints to Concessionaires and/or responses within 3 days upon receipt, and monitoring of Concessionaire action | Respond to and resolve stakeholder concerns on water supply, sewerage, and sanitation system operations. |  |  |  |  | -Assisted in the resolution of the issue in collaboration with the concerned personnel.
B. Support to Operations (STO)
Performance Indicator 1: Provision of technical information and support to other departments in the preparation and implementation of various COB funded projects and contracts
1.1 Waterproofing works of the roof decks of the MWSS Engineering and Administration Building | 100% assistance in the preparation and implementation of various COB-funded projects and contracts | Technical assistance in the monitoring of the project | RJVA/AME/MCMP |  |  |  | Assisted on technical review of TOR, plans and it request for procurement as well as on implementation. Posted on website last 03 February 2023 and issued NTP dated 15 September 2023.
1.2 MWSS Multi-Level Parking Project-Phase 2 (Design & Build) |  |  | FOMD Assigned Personnel |  |  |  | Assisted on technical review of TOR, plans and assistance during its implementation. Posted on website last 08 March 2024
1.4 Renovation of the Office Space at the 3rd Floor of the MWSS Engineering Building |  |  | FOMD Assigned Personnel |  |  |  | Assisted on technical review of TOR, plans and assistance during its implementation. Posted on website last 11 July 2023 and NTP was issued 01 January 2024.
Renovation Of The Fifth (5th) Floor Of The Mwss Administration Building |  |  | FOMD Assigned Personnel |  |  |  | Assisted on technical review of TOR, plans and assistance for its request for procurement
1.7 Removal of Existing Flooring and Installation of New Tiles at the Fourth (4th) Floor of MWSS Administration Building, MWSS Compound, Balara, Quezon City |  |  | ACH |  |  |  | Project completed on 25 January 2024 Assisted on technical review of TOR, plans and it request for procurement as well as on implementation. Issuance of NTP dated 27 September 2023
Performance Indicator 2: Client Satisfaction
2.1 Client Satisfaction Feedback |  | Submission of the Client Satisfaction Measurement Report every 1st Tuesday of the next month | FOMD
2.2 Updating of the FOMD Services in the Citizen's Charter |  | Submission to PPPRD | FOMD Assigned Personnel
C. General Administration and Support (GAS)
Performance Indicator 1: Support in the Procurement Activities in accordance with RA9184 and the procurenent guidelines of the lending institutions
1.1 Preparation and evaluation of documents for the procurement of items under COB of Infrastructure Projects, Goods, and Services
1.1.2 BAC - Technical Working Group | 100% accomplishment on the assigned task as BAC-TWG for infrastructure | Review TOR, Engineering plans, and Procurement documents | AME/MCMP |  |  |  | Assisted in the evaluation of TOR and Bids docs for various COB projects MWSS-BAC-M-24-235 MWSS-BAC-M-24-197 MWSS-BAC-M-24-220 MWSS-BAC-M-24-003
1.1.3 Final Inspection and Acceptance | 100% accomplishment inlcuding rectifications works and completion of punchlisting | FIAC - Chairperson Final Inspection and Acceptance Reports | AME/CAG/JGAB |  |  |  | Conducted inspections and assisted in the preparation of turnover of the projects
1.4 Leasing Committee | 100% assistance in various task of the committee | 100% Participation on the Leasing Committee | AME/FLFF |  |  |  | Assisted in the construction Pipelaying of Manila Water Company over the property of Philippine Nartional Railways (PNR) over MWSS
1.5 Disaster Control Committee | 100% assistance in various task of the committee | 100% Participation on the Disaster Control Committee | AME/CAG/MCMP/FLFF |  |  |  | Assisted in Procurement of Supply and Deliver of Community Outreach and Disaster Emergency Preparedness Kit (Contract No. MWSS-2023-KIT)
FINAL AVERAGE RATING
Legend: 1 - Quality, 2 - Efficiency, 3 - Timeliness
II. Signature approvals after performance monitoring, assessment, feedback by To be signed after the Performance Review and Feedback by the PMT
Prepared by: | Reviewed by: Dept. Mgr., PPPRD |  |  | Recommended by: ROMEO D. RODEROS Deputy Administrator, Management Services and Chairman, Performance Management Team |  |  | The final rating was discussed with the ratee. Approved and Rated by: LTGEN EMMANUEL B. SALAMAT (Ret) Administrator
ARCANGEL M. EUGENIO | RYAN JAMES V. AYSON |  |  | JOSE D. DORADO, JR. |  |  | LEONOR C. CLEOFAS, CESO IV
Division Manager A, East Zone Division | Department Manager, Field Operations Management Department |  |  | Deputy Administrator, Engineering and Technical Operations Group |  |  | Administrator
Rating of DA = Ave. of the opcr rating of the dept under the group
OPCR = IPCR of the Dept.